## PDR Objectives
PDR Objective (from IEEE 15288.2) | Priority 1 highest, 5 lowest | Prerequisite | Requirements | Requirement traceability | Requiremnt allocation | Requirement satisfaction evidence | Requirement verification | Interface control documents | Physical architecture (elements) | Physical architecture (interfaces) | Physical architecture (exchanges) | Physical architecture (interactions) | Development specifications | Design constraints | Trades | Technologies | Risks | Risk mitigation plans
a) All system-level functional and performance requirements baselined at SRR and SFR have been correctly decomposed or directly allocated to the lowest level of the specification tree for all system elements uniquely identified. | 1 | Requirements consistent with SRR/SFR maturity | X | X | X |  |  |  | X | X | X | X
i) Bi-directional traceability exists between the source requirements and the design elements for all decomposed and allocated requirements. | 1 |  | X | X | X |  |  |  | X | X | X | X
e) All external interfaces to the system, as defined at the SRR, have been documented in interface control documents. | 1 | Total system architecture | X |  |  |  |  | X | X | X
f) All system internal interfaces (system element to system element) have been documented in interface control documents. | 1 |  | X |  |  |  |  | X | X | X
j) All system hardware element physical architectures are complete. | 1 | [7 empty] | X | X
m) The set of system elements comprising the preliminary system design can achieve the complete set of allocated system baseline requirements, and forms a satisfactory basis for proceeding into detailed design with acceptable risk. | 2 | (Prioritize system reqt satisfaction) | X |  |  | X |  |  | X | X | X | X
d) The design as disclosed satisfies all requirements in the approved system specification. | 2 |  | X |  |  | X |  |  | X | X | X | X
g) The verification approach to demonstrate achievement of all allocated performance requirements has been documented. | 3 |  | X |  |  |  | X
h) All design constraints have been captured and incorporated into the allocated requirements and the design. | 3 |  | X |  | X |  |  |  | X |  |  |  |  | X
c) The allocated baseline is complete. | 4 |  | X | X | X | X |  |  | X | X |  |  | X
k) All system hardware element development specifications are complete. | 4 | [7 empty] | X | X | X | X | X
l) The software logical and physical architectures are complete to the extent specified in the SDP for the point in its life cycle at which PDR occurs, based on the selected life-cycle model(s). | 4 | [7 empty] | X | X | X | X | X
b) Sufficient requirements trades have been conducted, supported by systems engineering trade-off analyses, to influence the system physical architecture and allocated requirements. | 5 | Tradeoff objectives | X | [5 empty] | X | X |  |  |  |  | X
n) All critical technologies have been demonstrated in a relevant environment and can be integrated into a system with acceptable risk. | 5 | [7 empty] | X | [6 empty] | X
o) Risks have been identified and mitigation plans are in place. | 5 | [7 empty] | X | X | [6 empty] | X | X

## PDR Products
|  |  | R = Required to achieve Objective in MVM S = Supports Objective but is not required for MVM | Priority 1 highest, 5 lowest | a | i | e | f | j | m | d | g | h | c | k | l | b | n | o
# | 15288.2 para | Product | Description |  | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5
1 | 6.5.1 | PDR technical review products acceptability criteria | Table 13 lists the products that should be reviewed at PDR, and the associated acceptability criteria that should form a sufficient basis by which to assess each product’s content as acceptable to support a successful PDR. Specific products and associated acceptability criteria shall be deleted, modified, or additional items included, in accordance with the acquirer-supplier agreement, to support a given program. |  | 8 | 3 | 3 | 3 | 6 | 8 | 3 | 4 | 2 | 2 | 4 | 10 | 7 | 1 | 4
64 | 6.5.1.3.b | Technical plans | b) Integrating activities of any lower-level PDRs have occurred; identified issues are documented in action plans. | Assume satisfied | bar: i; m to d
4 | 6.5.1.1.c | System allocated baseline documentation | c) Interoperability functional performance requirements are allocated to all system, segment and subsystem preliminary designs. | 1 | bar: a to j; c
5 | 6.5.1.1.d | System allocated baseline documentation | d) Preliminary design satisfies design considerations and demonstrates consistency with a standard implementation framework such as department of defense architecture framework (DoDAF) 2.0 or equivalent. | 1 | bar: j; h to c
36 | 6.5.1.1.ii | System allocated baseline documentation | ii) Appropriate margins are established at the segment, subsystem, and component levels as applicable. | 1 | bar: a to i; c
37 | 6.5.1.1.jj | System allocated baseline documentation | jj) Requirements allocation and derivation from system to segment, subsystem and component levels are complete, traceable to the preliminary design and all “to be determined” (TBD) items are being tracked to resolution. | 1 | bar: a; c; b
38 | 6.5.1.1.kk | System allocated baseline documentation | kk) Interface definitions at the inter-segment and inter-subsystem levels are complete, documented, and traceable to the preliminary design and all TBDs are being tracked to resolution. | 1 | bar: e to f; c
41 | 6.5.1.1.nn | System allocated baseline documentation | nn) Key allocated performance requirements are traceable to the system’s preliminary design at the segment, subsystem, and component levels as applicable. | 1 | bar: a; c; b
42 | 6.5.1.1.oo | System allocated baseline documentation | oo) Key allocated performance requirement parameters developed and assessed at SFR are implemented in each major subsystem and component preliminary design. | 1 | bar: a; c; b
47 | 6.5.1.1.tt | System allocated baseline documentation | tt) Computer system and software logical architecture designs have been established; all computer SWCIs, HWCIs, computer software components (CSCs), and computer software units (CSUs) have been defined. | 1 | bar: j to d; c; l
56 | 6.5.1.1.ccc | System allocated baseline documentation | ccc) System allocated baseline documentation is sufficiently complete and correct to enable detailed design to proceed with proper CM. | 1 | bar: a to m; g to c
57 | 6.5.1.2.a | System functional or allocated baseline documentation | a) Preliminary design (hardware, software, human procedures), including interface descriptions is complete, satisfies all requirements in the system functional baseline and is under CM without any major TBDs or open items. | 1 | bar: a; e to m; c
62 | 6.5.1.2.f | System functional or allocated baseline documentation | f) Bi-directional requirements traceability among functional and allocated baselines and the preliminary design is complete, consistent, and has been approved by all applicable stakeholders. | 1 | bar: a to i; j to m; c
2 | 6.5.1.1.a | System allocated baseline documentation | a) Analysis of system performance is complete and is assessed to meet requirements traceable to the validated CDD. | 2 | bar: m to d; c
6 | 6.5.1.1.e | System allocated baseline documentation | e) System operational functions and environments for the preliminary design are traceable to the supplier’s CONOPS and the allocated baseline. | 2 | bar: m; c
54 | 6.5.1.1.aaa | System allocated baseline documentation | aaa) System end-to-end data flow is complete and documented in the preliminary design. | 2 | bar: a; e to d; c
107 | 6.5.1.5.a | Program life-cycle cost estimate | a) System cost model has been updated, allocated to lower system element levels, and tracked against targets; production cost model constructed. | 2 | bar: m; c
108 | 6.5.1.5.b | Program life-cycle cost estimate | b) Updated CARD is consistent with the proposed allocated baseline. | 2 | bar: m; c
68 | 6.5.1.3.f | Technical plans | f) Plans documenting the system, segment, subsystem, and component V&V approaches are developed for the preliminary design. | 3 | bar: g
69 | 6.5.1.3.g | Technical plans | g) Preliminary V&V plans are traceable to the preliminary design correlating all test objectives, test environments and test resources with allocated requirements. | 3 | bar: g
70 | 6.5.1.3.h | Technical plans | h) Preliminary V&V plans address data acquisition, reduction, analysis and documentation, and success criteria. | 3 | bar: g
48 | 6.5.1.1.uu | System allocated baseline documentation | uu) The preliminary design is consistent with the end-to-end processing capabilities and capacities needed for mission operations as indicated by the system performance analysis results. | 4 | bar: i; m to d; c; l
50 | 6.5.1.1.ww | System allocated baseline documentation | ww) Software requirements specifications (SRS) and interface requirement specifications (IRS), including verification plans, are complete and baselined for all SWCIs for the planned builds up to this point, and satisfy the system functional requirements. | 4 | bar: e to f; c; l
52 | 6.5.1.1.yy | System allocated baseline documentation | yy) Interface control documents trace all software interface requirements to the SWCIs and CSUs. | 4 | bar: e to f; c; l
53 | 6.5.1.1.zz | System allocated baseline documentation | zz) Preliminary software design has been defined and captured for the builds up to this point. | 4 | bar: c; l
73 | 6.5.1.3.k | Technical plans | k) Design development planning is completed and baselined. | 4 | bar: g; k to l
84 | 6.5.1.3.v | Technical plans | v) Software plans have sufficient content to demonstrate that | 4 | bar: l
85 | 6.5.1.3.v.1 | Technical plans | 1) Computer systems and software design and development approach have been confirmed through analyses, demonstrations, and prototyping in a relevant environment. | 4 | bar: l
86 | 6.5.1.3.v.2 | Technical plans | 2) Software increments have been defined and capabilities allocated to specific increments. | 4 | bar: l
87 | 6.5.1.3.v.3 | Technical plans | 3) Software trade studies addressing COTS, reuse, and other software-related issues are completed. | 4 | bar: l to b
88 | 6.5.1.3.v.4 | Technical plans | 4) Software development process is defined in a baselined software development plan and reflected in the IMP and IMS. | 4 | bar: l
89 | 6.5.1.3.v.5 | Technical plans | 5) Software development schedules reflect supplier software processes and IMP/IMS software events for current and future development phases. | 4 | bar: l
90 | 6.5.1.3.v.6 | Technical plans | 6) Software development environment and test/integration labs have been established with sufficient fidelity and capacity. | 4 | bar: l
91 | 6.5.1.3.v.7 | Technical plans | 7) Software metrics have been defined and a reporting process has been implemented; metrics are being actively tracked and assessed. | 4 | bar: l
92 | 6.5.1.3.v.8 | Technical plans | 8) Testability requirements―built-in test (BIT), false alarm rate, fault isolation, fault detection―have been identified and the required software support documented as requirements so that they can be tested in the proposed design. | 4 | bar: l
93 | 6.5.1.3.v.9 | Technical plans | 9) TEMP addresses all SWCI plans, test facilities, and test plans, including testing required to support incremental approaches and regression tests. | 4 | bar: l
94 | 6.5.1.3.v.10 | Technical plans | 10) Software development estimates [i.e., size, effort (cost), and schedule] are updated. | 4 | bar: l
95 | 6.5.1.3.w | Technical plans | w) Hardware plans have sufficient content to demonstrate that | 4 | bar: k
96 | 6.5.1.3.w.1 | Technical plans | 1) The hardware design/development approach has been confirmed through analyses, demonstrations, and prototyping in a relevant environment. | 4 | bar: k
97 | 6.5.1.3.w.2 | Technical plans | 2) Hardware trade studies addressing COTS, reuse, and other software-related issues are completed. | 4 | bar: k; b
98 | 6.5.1.3.w.3 | Technical plans | 3) The major phases of the program’s hardware design and development process are defined in a hardware development plan and reflected in the IMP and IMS. | 4 | bar: k
99 | 6.5.1.3.w.4 | Technical plans | 4) Hardware development schedules reflect supplier hardware processes and IMP/IMS hardware design and development events. | 4 | bar: k
100 | 6.5.1.3.w.5 | Technical plans | 5) Hardware development environment (e.g., computer modeling and design tools) and test/integration labs have been established with sufficient fidelity and capacity. | 4 | bar: k
101 | 6.5.1.3.w.6 | Technical plans | 6) Hardware metrics have been defined and a reporting process has been implemented; metrics are being actively tracked and assessed. | 4 | bar: k
102 | 6.5.1.3.w.7 | Technical plans | 7) R&M and testability requirements―BIT, false alarm rate, fault isolation, fault detection―have been identified and the required hardware support documented as requirements so that they can be tested in the proposed design. Also, requirements for detailed design have been identified such as thermal, vibration, shock environments, and highly accelerated life testing (HALT). | 4 | bar: k
103 | 6.5.1.3.w.8 | Technical plans | 8) TEMP addresses all HWCI plans, test facilities, and test plans, including testing required to support incremental approaches and regression tests. | 4 | bar: k
104 | 6.5.1.3.w.9 | Technical plans | 9) Hardware development estimates [i.e., number of HWCIs, effort (cost) and schedule] are updated. | 4 | bar: k
3 | 6.5.1.1.b | System allocated baseline documentation | b) Trade studies related to the design of the system and its lowest level specified CIs are complete and documented, including the rationale for selection of the preferred alternative. | 5 | bar: c; b
7 | 6.5.1.1.f | System allocated baseline documentation | f) Preliminary system-level design is producible and assessed to be within the production budget. | 5 | bar: c
8 | 6.5.1.1.g | System allocated baseline documentation | g) Preliminary long lead production requirements are developed and documented. | 5 | bar: c
9 | 6.5.1.1.h | System allocated baseline documentation | h) PM&P allocated requirements are incorporated into the preliminary design. | 5 | bar: c
10 | 6.5.1.1.i | System allocated baseline documentation | i) Mass properties margins (average or complex) are established for PDR and correlated with the preliminary design, including allowable growth allocations and metrics. | 5 | bar: c
11 | 6.5.1.1.j | System allocated baseline documentation | j) SSE, COMSEC, cybersecurity, and PP security requirements are allocated and incorporated into the preliminary design in accordance with DoD policies, directives, and system specifications. | 5 | bar: c
12 | 6.5.1.1.k | System allocated baseline documentation | k) EMI control processes and procedures are developed for the preliminary design, and EMI/EMC allocated requirements are incorporated into the preliminary design. | 5 | bar: c
13 | 6.5.1.1.l | System allocated baseline documentation | l) User interface hardware and software allocated requirements for operators, users, maintainers, and sustainers are incorporated into the preliminary design. | 5 | bar: c
14 | 6.5.1.1.m | System allocated baseline documentation | m) Contamination control processes and procedures are developed for the preliminary design. | 5 | bar: c
15 | 6.5.1.1.n | System allocated baseline documentation | n) Hazardous materials management and pollution prevention allocate requirements are incorporated into the preliminary design. | 5 | bar: c
16 | 6.5.1.1.o | System allocated baseline documentation | o) Data storage analysis identifies reliability, maintainability, and availability requirements for storage systems environments. | 5 | bar: c
17 | 6.5.1.1.p | System allocated baseline documentation | p) The preliminary data storage physical architecture fully addresses elements, including communications and processing capacity. | 5 | bar: c
18 | 6.5.1.1.q | System allocated baseline documentation | q) The data storage logical architecture defines a complete list of data receivers to include both computer and human agents. | 5 | bar: c
19 | 6.5.1.1.r | System allocated baseline documentation | r) The level of user integrity (e.g., access control lists) has been identified that enables the system requirements to be met. | 5 | bar: c
20 | 6.5.1.1.s | System allocated baseline documentation | s) DT&E elements are correlated with the preliminary design. | 5 | bar: c; n
21 | 6.5.1.1.t | System allocated baseline documentation | t) OT&E allocated requirements are incorporated into the preliminary design. | 5 | bar: c
22 | 6.5.1.1.u | System allocated baseline documentation | u) Assessment of the technical effort and design indicates potential for OT&E success (operationally effective and suitable). | 5 | bar: c
23 | 6.5.1.1.v | System allocated baseline documentation | v) The preliminary design incorporates all survivability, vulnerability, and threat allocated requirements for all categories of expected threats, threat environments and their likelihood of occurrence. | 5 | bar: c; o
24 | 6.5.1.1.w | System allocated baseline documentation | w) A draft critical technologies list is documented. | 5 | bar: c; n
25 | 6.5.1.1.x | System allocated baseline documentation | x) All CSIs and CAIs are identified. | 5 | bar: c; o
26 | 6.5.1.1.y | System allocated baseline documentation | y) System safety allocated requirements are incorporated into the preliminary design. | 5 | bar: c; o
27 | 6.5.1.1.z | System allocated baseline documentation | z) Preliminary hazard analyses are completed and a prioritized list of safety hazards is documented. | 5 | bar: c; o
28 | 6.5.1.1.aa | System allocated baseline documentation | aa) ESOH allocated requirements are incorporated into the preliminary design. | 5 | bar: c; o
29 | 6.5.1.1.bb | System allocated baseline documentation | bb) Functional failure modes, effects, and criticality analysis (FMECA) is completed. | 5 | bar: c; o
30 | 6.5.1.1.cc | System allocated baseline documentation | cc) R&M allocated requirements are supported by the preliminary design. | 5 | bar: c
31 | 6.5.1.1.dd | System allocated baseline documentation | dd) Program’s reliability growth planning strategy and growth curve supports key program milestones needed to meet the CDD threshold at initial operational test and evaluation (IOT&E), and is adequate to grow to the specification value, considering the test schedule and resources. | 5 | bar: c
32 | 6.5.1.1.ee | System allocated baseline documentation | ee) Results from the R&M analyses are used in O&S cost estimates, availability analyses, provisioning plans (spares and repair parts), and maintenance concept. | 5 | bar: c
33 | 6.5.1.1.ff | System allocated baseline documentation | ff) Environmental qualification requirements are incorporated into the design and are addressed in the requirements traceability documentation. | 5 | bar: i; h to c
34 | 6.5.1.1.gg | System allocated baseline documentation | gg) Estimate of system reliability and maintainability is updated, based on engineering analyses, initial test results, or other sources of demonstrated reliability and maintainability. | 5 | bar: c
35 | 6.5.1.1.hh | System allocated baseline documentation | hh) Quality and product assurance allocated requirements are incorporated into the preliminary design. | 5 | bar: i; c
39 | 6.5.1.1.ll | System allocated baseline documentation | ll) Preliminary ground support equipment designs if applicable are traceable to the system allocated baseline and to the preliminary design. | 5 | bar: m to d; c
40 | 6.5.1.1.mm | System allocated baseline documentation | mm) Supportability allocated requirements are incorporated into the preliminary design. | 5 | bar: a to i; c
43 | 6.5.1.1.pp | System allocated baseline documentation | pp) All deficiencies identified as a result of any testing performed to date, including those related to technology deficiencies identified at SFR, have been correlated with the applicable portions of the preliminary design, impacts have been assessed, and candidate design changes to correct the deficiencies have been identified. | 5 | bar: m to d; c; o
44 | 6.5.1.1.qq | System allocated baseline documentation | qq) The documented results of any prototyping done to date provide evidence that the technical approach is adequate and the risk levels for the corresponding design approach are acceptable. | 5 | bar: c; n to o
45 | 6.5.1.1.rr | System allocated baseline documentation | rr) Prototypes implemented to date correctly implement the corresponding portions of the functional baseline and are consistent with the preliminary physical architecture. | 5 | bar: a to i; m to d; c
46 | 6.5.1.1.ss | System allocated baseline documentation | ss) The physical and functional interfaces of each prototype implemented to date satisfy the corresponding allocated requirements, and validate the sufficiency of the applicable external interface requirements levied on the system for its interaction with facilities and personnel. | 5 | bar: a to f; m to d; c
49 | 6.5.1.1.vv | System allocated baseline documentation | vv) Preliminary growth margin requirements are documented for computer resources (memory and storage capacity, processor throughput, communications bandwidth, etc.) | 5 | bar: a to i; m to d; c; l
51 | 6.5.1.1.xx | System allocated baseline documentation | xx) Software functionality in the preliminary design is consistent with resources expended per the IMS and the software metrics. | 5 | bar: c; l
55 | 6.5.1.1.bbb | System allocated baseline documentation | bbb) All required software-related documents are baselined and delivered for the builds up to this point. | 5 | bar: c; l
58 | 6.5.1.2.b | System functional or allocated baseline documentation | b) System, segment, subsystem, and component-level interfaces are baselined and are under configuration control. | 5 | bar: a to f; c
59 | 6.5.1.2.c | System functional or allocated baseline documentation | c) C4I allocations are incorporated into the preliminary design across segments, subsystems, and components. | 5 | bar: a to i; c
60 | 6.5.1.2.d | System functional or allocated baseline documentation | d) The threat scenario operational and environmental allocations are incorporated into the preliminary design and are traceable to all segments, subsystems, and components. | 5 | bar: a to i; c; o
61 | 6.5.1.2.e | System functional or allocated baseline documentation | e) Test requirements and test data collected to date for the preliminary design are traceable to operational requirements via specifications and VCRMs. | 5 | bar: g; c
63 | 6.5.1.3.a | Technical plans | a) Supplier’s SEMP is complete, adequate and aligned with the program SEP. | 5
65 | 6.5.1.3.c | Technical plans | c) Plan to CDR is accurately documented in the SEP and SEMP, as well as in the IMP and IMS. | 5
66 | 6.5.1.3.d | Technical plans | d) Program is properly staffed by both the acquirer and supplier. | 5
67 | 6.5.1.3.e | Technical plans | e) Technical performance measures have been identified to track technical progression of design maturity concern areas. | 5 | bar: m to d; o
71 | 6.5.1.3.i | Technical plans | i) Hazardous materials management and pollution prevention processes and procedures are verified and baselined. | 5 | bar: o
72 | 6.5.1.3.j | Technical plans | j) Test bed(s) and test facilities chosen based on the preliminary design are deemed adequate to perform system, segment, subsystem, and interface requirements verification (e.g., for critical HWCIs and SWCIs, arrangements for procuring and scheduling the use of V&V resources―simulators, test beds, test facilities―have been demonstrated). | 5 | bar: g
74 | 6.5.1.3.l | Technical plans | l) Program schedule, as depicted in the updated IMS is executable within acceptable technical and cost risks. | 5 | bar: g; o
75 | 6.5.1.3.m | Technical plans | m) Program is executable with the existing budget. | 5 | bar: g; o
76 | 6.5.1.3.n | Technical plans | n) Trade studies and system producibility assessments are under way. | 5 | bar: b; o
77 | 6.5.1.3.o | Technical plans | o) All critical manufacturing processes have been defined, characterized, and documented. | 5 | bar: o
78 | 6.5.1.3.p | Technical plans | p) Failure reporting and corrective action system (FRACAS) is established. | 5 | bar: o
79 | 6.5.1.3.q | Technical plans | q) Logistics (sustainment) and training systems planning and documentation are sufficiently complete to support the technical review. | 5 | bar: o
80 | 6.5.1.3.r | Technical plans | r) LCSP is approved, including updates on program sustainment development efforts and schedules based on current budgets and firm supportability design features. | 5 | bar: o
81 | 6.5.1.3.s | Technical plans | s) LCSP includes software support requirements. | 5 | bar: o
82 | 6.5.1.3.t | Technical plans | t) LCSP addresses DMS, PM&P guidelines, and counterfeit parts risk management. | 5 | bar: o
83 | 6.5.1.3.u | Technical plans | u) Long-lead and key supply chain elements are identified, to include strategic materials risk. | 5 | bar: o
105 | 6.5.1.4.a | Problem risk assessment | a) Cost, schedule, and technical risks are identified, and mitigation plans are in place. | 5 | bar: o
106 | 6.5.1.4.b | Problem risk assessment | b) Risk management process is in place demonstrated by documented execution results of existing mitigation plans. | 5 | bar: o

## PDR Model Content
|  | Priority 1 highest, 5 lowest | a | i | e | f | j | m | d | g | h | c | k | l | b | n | o | Univ 1 Space Segment | Univ 2 Ground Segment | Univ 3 Integrated System
|  |  | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5
Requirement | System Requirement | Element | [17 empty] | 1 | bar: a to i; m to g
| Segment Requirement | Element | [15 empty] | 1 | 1 | 2 | bar: a to i; m to g
| Subsystem Requirement | Element | [15 empty] | 3 | 3 | bar: a to i; m; g
| Component Requirement | Element | bar: a to i; m; g
| Interface Requirement | Element | [15 empty] | 1 | 1 | 1 | bar: a to f; m; g
| Functional Requirement | Element | [15 empty] | 1 | 1 | 1 | bar: a to i; m
| Performance Requirement | Element | [15 empty] | 2 | 2 | 2 | bar: a to i; m; g
| Non-Functional Requirement | Element | [15 empty] | 3 | 3 | 3 | bar: i; m
| Verification Requirement | Element | [15 empty] | 8 | 8 | 8 | bar: g
| Work Requirement | Element
| Data Requirement | Element
| Requirement Flowdown (Complete) | Relation | [15 empty] | 2 | 2 | 2 | bar: a to i
| Requirement Flowdown (Partial) | Relation | [15 empty] | 2 | 2 | 2 | bar: a to i
| Requirement Derivation (Complete) | Relation | [15 empty] | 2 | 2 | 2 | bar: a to i
| Requirement Derivation (Partial) | Relation | [15 empty] | 2 | 2 | 2 | bar: a to i
| Requirement Decomposition (Complete) | Relation | [15 empty] | 2 | 2 | 2 | bar: a to i
| Requirement Decomposition (Partial) | Relation | [15 empty] | 2 | 2 | 2 | bar: a to i
Element | External System Element | Element | [17 empty] | 1 | bar: e; j
| System Element | Element | [15 empty] | 1 | 1 | 1 | bar: a to e; j to m
| Segment Element | Element | [15 empty] | 1 | 1 | 1 | bar: a to m
| Subsystem Element | Element | [15 empty] | 2 | 2 | bar: a to m
| Component Element | Element | [15 empty] | 5 | 5 | bar: a to i; f to m
| Configuration Item | Element | [15 empty] | 5 | 5 | bar: a to i; j to m
| Element Connection (Permanent) | Relation | [15 empty] | 3 | 3 | 3 | bar: j to m
| Element Connection (Potential) | Relation | [15 empty] | 3 | 3 | 3 | bar: j to m
Requirement-Element | Requirement Allocation (Complete) | Relation | [15 empty] | 4 | 4 | 4 | bar: a to i; m
| Requirement Allocation (Partial) | Relation | [15 empty] | 4 | 4 | 4 | bar: a to i; m
| Requirement Satisfaction (Complete) | Relation | [15 empty] | 9 | 9 | 9 | bar: d
| Requirement Satisfaction (Partial) | Relation | [15 empty] | 9 | 9 | 9 | bar: d
Interface | External Interface | Element | [15 empty] | 5 | 5 | 5 | bar: e; j to m
| Internal Interface | Element | [15 empty] | 5 | 5 | 5 | bar: f to m
| Interface Equivalence | Relation | [15 empty] | 5 | 5 | 5 | bar: j to m
| Interface Allocation | Relation | [15 empty] | 5 | 5 | 5 | bar: j to m
Requirement-Interface | Requirement Allocation (Complete) | Relation | [15 empty] | 5 | 5 | 5 | bar: e to f; m
| Requirement Allocation (Partial) | Relation | [15 empty] | 5 | 5 | 5 | bar: e to f; m
Exchange Item | Data Item | Element | [15 empty] | 6 | 6 | 6 | bar: e to j
| Material Item | Element | [15 empty] | 6 | 6 | 6 | bar: e to j
State |  | Element | [15 empty] | 7 | 7 | 7 | bar: a to i; j
State Transition |  | Relation | [15 empty] | 7 | 7 | 7 | bar: a to i; j
Mode |  | Element | [15 empty] | 7 | 7 | 7 | bar: a to i; j
Mode Transition |  | Relation | [15 empty] | 7 | 7 | 7 | bar: a to i; j
Function |  | Element | [15 empty] | 7 | 7 | 7 | bar: a to i; j
Signal |  | Element | [15 empty] | 7 | 7 | 7 | bar: a to i; j
Artifact | Interface Control Document/Specification | Element | [15 empty] | 5 | 5 | 5 | bar: e to f
Environment | Operational Environment | Element | [15 empty] | 1 | 1 | 1
| Test Environment | Element | [15 empty] | 8 | 8 | 8
| Analysis Environment | Element | [15 empty] | 8 | 8 | 8
Verification Activity | Analysis | Element | [15 empty] | 8 | 8 | 8 | bar: g
| Test | Element | [15 empty] | 8 | 8 | 8 | bar: g
| Inspection | Element | [15 empty] | 8 | 8 | 8 | bar: g
| Demonstration | Element | [15 empty] | 8 | 8 | 8 | bar: g
Requirement-Verification | Requirement Verified By (Complete) | Relation | [15 empty] | 8 | 8 | 8 | bar: g
| Requirement Verified By (Partial) | Relation | [15 empty] | 8 | 8 | 8 | bar: g
Constraint | Test Constraint | Element | [15 empty] | 8 | 8 | 8 | bar: g
| Design Constraint | Element | [15 empty] | 9 | 9 | 9 | bar: h
| Operational Constraint | Element | [15 empty] | 9 | 9 | 9 | bar: h
| Constraint Allocation (Complete) | Relation | [15 empty] | 9 | 9 | 9 | bar: h
| Constraint Allocation (Partial) | Relation | [15 empty] | 9 | 9 | 9 | bar: h
TBD |  | Element | [15 empty] | 9 | 9 | 9 | bar: a; d to g
Measure | Performance Measure | Element | [15 empty] | 9 | 9 | 9 | bar: a; d to g
| Performance Margin | Element | [15 empty] | 9 | 9 | 9 | bar: a; d to g

## PDR Questions
# | Question | a | i | e | f | j | m | d | g | h | c | k | l | b | n | o | Product | Increment | Sequence | Question |  |  | Team Assigned |  |  | Integration Demo
|  | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 |  |  |  | Team 1 | Team 2 | Team 3 | 1 | 2 | 3 | 1-2 | 1-3 | 2-3
1.01 | What are all the system-level requirements? | 1 | 1 | [14 empty] | 1 | 1 |  |  |  | o | o | X |  | X | X
1.02 | What are all the system-level functional requirements? | 1 | 1 | [14 empty] | 1 | 1 | [5 empty] | X |  | X
1.04 | What are all the segments belonging to the system? | 1 | 1 | [14 empty] | 1 | 1 |  |  |  | X | X | X |  | X | X
1.05 | What are all the segment-level requirements? | 1 | 1 | [14 empty] | 1 | 1 |  |  |  | X | X |  |  | X | X
1.06 | What are all the segment-level functional requirements? | 1 | 1 | [14 empty] | 1 | 1 |  |  |  | X | X |  |  | X
1.15 | What is the product breakdown structure of the system into segments (and elements not owned by a segment)? | 2 | 2 |  |  | 2 | [11 empty] | 1 | 1 |  |  |  | X | X |  |  | X | X
1.03 | What are all the system-level performance requirements? | 1 | 1 | [14 empty] | 1 | 2 | [5 empty] | X |  |  | X
1.07 | What are all the segment-level performance requirements? | 1 | 1 | [14 empty] | 1 | 2 |  |  |  | X | X |  |  |  | X
1.08 | Have all system-level requirements been fully decomposed to appropriate segment-level requirements? | 1 | 1 | [14 empty] | 1 | 2 |  |  |  | X |  |  |  | X
1.09 | Has each system-level requirement been fully decomposed (without gaps) into appropriate segment-level requirements? | 1 | 1 | [14 empty] | 1 | 2 |  |  |  | X |  |  |  | X
1.1 | Has each segment-level requirement been traced to its appropriate source(s)? | 2 | 2 | [14 empty] | 1 | 2 |  |  |  | X |  |  |  | X
1.11 | Has each segment-level requirement been traced to its parent system-level requirement(s)? | 2 | 2 | [14 empty] | 1 | 2 |  |  |  | X |  |  |  | X
1.14 | Has each performance requirement been traced to each relevant functional requirement? | 3 | 3 | [14 empty] | 1 | 2 |  |  |  | X | X |  |  | X | X
1.16 | What is the product breakdown structure of each segment into segment elements or subsystems? | 2 | 2 |  |  | 2 | [11 empty] | 1 | 2 |  |  |  | X | X |  |  | X | X
1.24 | What are all the subsystems belonging to the segment? | 3 | 3 |  |  | 3 | [11 empty] | 1 | 2 |  |  |  | X | X
1.25 | What are all the subsystem-level requirements? | 3 | 3 | [14 empty] | 1 | 3 |  |  |  | X | X
1.26 | What are all the subsystem-level functional requirements? | 3 | 3 | [14 empty] | 1 | 3 |  |  |  | X | X
1.27 | What are all the subsystem-level performance requirements? | 3 | 3 | [14 empty] | 1 | 3 |  |  |  | X | X
1.28 | What are all the subsystem requirements? | 3 | 3 | [14 empty] | 1 | 3 |  |  |  | X | X
1.12 | Has each system-level requirement been allocated to the appropriate system and/or segment element(s)? | 2 | 2 | [14 empty] | 1 | 4 |  |  |  | X |  |  |  | X
1.13 | Has each segment-level requirement been allocated to the appropriate segment element(s)? | 2 | 2 | [14 empty] | 1 | 4 |  |  |  | X |  |  |  | X
1.17 | What are all the requirements allocated to the system in the model? | 2 | 2 | [14 empty] | 1 | 4 | [5 empty] | X
1.18 | What are all the requirements allocated to the segment in the model? | 2 | 2 | [14 empty] | 1 | 4 |  |  |  | X | X |  |  | X | X
1.19 | Have all necessary system-level requirements been identified? | 2 | 2 | [14 empty] | 1 | 4
1.2 | For each segment, have all necessary system-level requirements been allocated to it? | 2 | 2 | [14 empty] | 1 | 4
1.21 | For each subsystem, have all necessary segment-level requirements been allocated to it? | 2 | 2 | [14 empty] | 1 | 4
1.22 | Have all necessary segment-level requirements been identified? | 3 | 3 | [14 empty] | 1 | 4
1.23 | For each system-level requirement, has it been correctly decomposed or directly allocated to the lowest level of the specification tree for all system elements uniquely identified? | 1 | 1 | [14 empty] | 1 | 4 | [5 empty] | X |  | X | X
1.29 | Have all segment-level requirements been fully decomposed to appropriate subsystem-level requirements? | 3 | 3 | [14 empty] | 1 | 4 |  |  |  | X | X
1.3 | Have all segment-level requirements been fully decomposed to appropriate subsystem-level requirements? | 3 | 3 | [14 empty] | 1 | 4
1.31 | Has each segment-level requirement been fully decomposed (without gaps) into appropriate subsystem-level requirements? | 4 | 4 | [14 empty] | 1 | 4 |  |  |  |  | X |  |  |  | X
1.32 | Has each subsystem-level requirement been traced to its appropriate source(s)? | 4 | 4 | [14 empty] | 1 | 4 |  |  |  |  | X |  |  |  | X
1.33 | Has each subsystem-level requirement been traced to its parent segment-level requirement(s)? | 4 | 4 | [14 empty] | 1 | 4 |  |  |  |  | X |  |  |  | X
1.34 | Has each segment-level requirement been allocated to the appropriate system and/or subsystem element(s)? | 4 | 4 | [14 empty] | 1 | 4 |  |  |  |  | X |  |  |  | X
1.35 | Has each subsystem-level requirement been allocated to the appropriate subsystem element(s)? | 4 | 4 | [14 empty] | 1 | 4 |  |  |  |  | X |  |  |  | X
1.36 | What are all the requirements allocated to the subsystem in the model? | 4 | 4 | [14 empty] | 1 | 4
1.37 | What are all the external/internal interfaces? |  |  | 5 | 5 | 5 | [11 empty] | 2 | 5 |  |  |  | X | X | X | X | X | X
1.38 | What are all the required external/internal interfaces? |  |  | 5 | 5 | 5 | [11 empty] | 2 | 5 |  |  |  | X | X | X | X | X | X
1.39 | What are all the external/internal interface requirements? |  |  | 5 | 5 | [12 empty] | 2 | 5 |  |  |  | X | X | X | X | X | X
1.4 | Which interface requirements apply to each external/internal interface? |  |  | 5 | 5 | [12 empty] | 2 | 5 |  |  |  | X | X | X | X | X | X
1.41 | Which external/internal interfaces are subject to each external interface requirement? |  |  | 5 | 5 | [12 empty] | 2 | 5 |  |  |  | X | X | X | X | X | X
1.42 | What resources flow across each external/internal interface? |  |  | 5 | 5 | 5 | [11 empty] | 2 | 5 |  |  |  | X | X | X | X | X | X
1.43 | Which external/internal interfaces are needed to implement each use case or mission thread? |  |  | 6 | 6 | [12 empty] | 2 | 6 |  |  |  | X | X | X | X | X | X
1.44 | Has each external/interface interface been adequately defined? |  |  | 6 | 6 | [12 empty] | 2 | 6 |  |  |  | X | X | X | X | X | X
1.45 | Have all external/internal interfaces been adequately defined? |  |  | 6 | 6 | [12 empty] | 2 | 6 |  |  |  | X | X | X | X | X | X
1.46 | What connections are required between segments? |  |  | 6 | 6 | [12 empty] | 2 | 6 |  |  |  | X | X | X | X | X | X
1.47 | What connections are required between subsystems? |  |  | 6 | 6 | [12 empty] | 2 | 6 |  |  |  | X | X
1.48 | What resources flow across each connection? |  |  | 6 | 6 | [12 empty] | 2 | 6 |  |  |  | X | X | X
1.49 | What external systems are required of the system? |  |  | 6 | 6 | [12 empty] | 2 | 6 | [5 empty] | X
1.5 | What external systems are required of each segment? |  |  | 6 | 6 | [12 empty] | 2 | 6 |  |  |  | X | X | X |  | X | X
1.51 | What functions are required of the system? |  |  |  |  | 7 | [11 empty] | 2 | 7 | [5 empty] | X |  | X | X
1.52 | What functions are required of each segment? |  |  |  |  | 7 | [11 empty] | 2 | 7 |  |  |  | X | X | X | X | X | X
1.53 | What functions are required of each subsystem? |  |  |  |  | 7 | [11 empty] | 2 | 7 |  |  |  | X | X
1.54 | Which functional requirements apply to each function? |  |  |  |  | 7 | [11 empty] | 2 | 7 |  |  |  | X | X
1.55 | What are the modes of operation of the system? |  |  |  |  | 8 | [11 empty] | 2 | 8 | [5 empty] | X |  | X | X
1.56 | What are the modes of operation of each segment? |  |  |  |  | 8 | [11 empty] | 2 | 8 |  |  |  | X | X | X | X | X | X
1.57 | What are the modes of operation of each subsystem? |  |  |  |  | 8 | [11 empty] | 2 | 8 |  |  |  | X | X
1.58 | Which functional requirements apply to each mode of operation? |  |  |  |  | 8 | [11 empty] | 2 | 8 |  |  |  | X | X
1.59 | What are the interactions between segments? |  |  |  |  | 8 | [11 empty] | 2 | 8 |  |  |  | X | X
1.6 | What are the interactions between subsystems? |  |  |  |  | 8 | [11 empty] | 2 | 8 |  |  |  | X | X
1.61 | Which functional requirements apply to each interaction? |  |  |  |  | 8 | [11 empty] | 2 | 8 |  |  |  | X | X
1.62 | What is the required behavior of the system? |  |  |  |  | 9 | [11 empty] | 2 | 9 | [5 empty] | X |  | X | X
1.63 | What is the required behavior of each segment? |  |  |  |  | 9 | [11 empty] | 2 | 9 |  |  |  | X | X | X | X | X | X
1.64 | What is the required behavior of each subsystem? |  |  |  |  | 9 | [11 empty] | 2 | 9 |  |  |  | X | X
1.65 | What are the components within each subsystem? | [5 empty] | 10 | [10 empty] | 3 | 10 |  |  |  | X | X
1.63 | What are the connections between components wtihin each subsystem? | [5 empty] | 10 | [10 empty] | 3 | 10 |  |  |  | X | X
1.64 | Does the performance of the system satisfy its performance requirements? | [6 empty] | 11 | [9 empty] | 3 | 11 | [7 empty] | X | X
1.635 | Does the performance of each segment satisfy its performance requirements? | [6 empty] | 11 | [9 empty] | 3 | 11 | [6 empty] | X | X | X
1.633 | Does the performance of each subsystem satisfy its performance requirements? | [6 empty] | 11 | [9 empty] | 3 | 11 | [6 empty] | X | X

## PDR Question Matrix
| Identity | System level requirements | Segment level requirements | System-level functional requirements | System-level performance requirements | Segment-level functional requirements | Segment-level performance requirements | Requirement source | Requirement decomposition | Requirement allocation | System architecture | Segment architecture
System level requirements | 1.01 |  | 1.08
Segment level requirements | 1.05
System-level functional requirements | 1.02
System-level performance requirements | 1.03
Segment-level functional requirements | 1.06
Segment-level performance requirements | 1.04
Requirement source | 1.07
Requirement decomposition
Requirement allocation
System architecture
Segment architecture

## PDR Entry
5.5.4 | The PDR shall be conducted only after the following events have been successfully completed:
5.5.4.a | a) The acceptability criteria for each of the PDR technical review products have been established for the specific program by tailoring the contents of Clause 6, Table 13.
5.5.4.b | b) All preparatory actions in Clause 6, Table 14 as tailored for the specific program have been successfully accomplished to support conducting the technical review.
5.5.4.c | c) The acquirer and supplier concur that the allocated baseline and the program budget estimate are sufficiently mature to support the case for a successful PDR as judged against the tailored product acceptance criteria.
5.5.4.d | d) Any prior system element level or incremental PDRs on which this PDR is dependent have been completed and their action items closed, or documented action items required for closure are acknowledged.

## PDR Exit
5.5.6 | The PDR shall be deemed completed only after the following events have been successfully completed:
5.5.6.a | a) All action items submitted during the technical review have been appropriately addressed.
5.5.6.b | b) All actions listed in the action items required for review closure have been completed and approved by the required parties.
5.5.6.c | c) The content of corrective action plans for issues identified in the PDR is sufficiently complete and unambiguous to enable successful completion of all corrective actions.
5.5.6.d | d) Each of the technical review products listed in Clause 6, Table 13 as tailored for the specific program meets all of its acceptability criteria, or has a corrective action plan documenting the corrective actions required to achieve acceptability.
5.5.6.e | e) The acquirer and supplier concur that the program risk level is acceptable.
5.5.6.f | f) All affected baselines have been updated in the applicable CM system(s).
5.5.6.g | g) The PDR chair formally closes the review.

## PDR Outputs
5.5.5.3 | PDR outputs
5.5.5.3.a | a) The review team shall document sufficient assessment results to show the program has produced
5.5.5.3.a.1 | 1) Technical data for the allocated baseline that are complete, satisfy the system specification, and provide a sufficient foundation for detailed design to proceed.
5.5.5.3.a.2 | 2) Bi-directional traceability between all decomposed and allocated requirements to the lowest level of the specification tree, demonstrating that each and every function in the functional baseline has been allocated to one or more of the system elements, that the physical hierarchy is consistent with the functional baseline, and that there are no orphan system elements.
5.5.5.3.a.3 | 3) Technical plans that are current and address the full scope of work.
5.5.5.3.a.4 | 4) An updated (if necessary) risk and opportunity assessment, and associated risk mitigation and opportunity handling plans.
5.5.5.3.a.5 | 5) Feasibility, budget, and schedule that are determined to be within acceptable risk margins.
5.5.5.3.a.6 | 6) A program IMS that has been updated (including systems and software critical path drivers) and includes all activities required to complete CDR (assuming same developer responsible for PDR and CDR).
5.5.5.3.a.7 | 7) Updates to the CARD that reflect the design in the allocated baseline.
5.5.5.3.a.8 | 8) Evidence to inform realistic requirements for EMD contract specifications.
5.5.5.3.a.9 | 9) Interface requirements contained in system external interface control documentation and internal interface control documentation.
5.5.5.3.b | b) The PDR technical review summary report shall be distributed containing the following attachments:
5.5.5.3.b.1 | 1) List of attendees
5.5.5.3.b.2 | 2) Final copies of all presentations
5.5.5.3.b.3 | 3) Updated (if necessary) risk assessment, mitigation plans, and opportunity handling plans
5.5.5.3.b.4 | 4) Documented action items including those required for closure
5.5.5.3.b.5 | 5) The tailored Clause 6, Table 13 through Table 16 as completed following the technical review
5.5.5.3.b.6 | 6) Meeting minutes

## PDR Roles
6.5.2 | PDR preparation | Table 14 lists the actions that should be considered during preparation for the PDR. The responsible people listed are those most often tasked with the listed preparation actions, but the acquirer and supplier may agree to assign the actions to different people or organizations depending on a given program’s organizational structure. Specific actions shall be deleted, modified, or additional items included, in accordance with the acquirer-supplier agreement, to support a given program. Responsibilities shall be assigned to people or organizations in accordance with the acquirer-supplier agreement.
6.5.2.1.a | Program manager | a) Approve, fund, and staff the system PDR as planned in the SEP developed by the systems engineer.
6.5.2.1.b | Program manager | b) Manage and approve changes to the segment, subsystem and system element development specifications well enough in advance to allow successful execution of the PDR delivery of an acceptable allocated baseline at the PDR.
6.5.2.1.c | Program manager | c) Establish the plan to CDR in applicable contract documents including the SEMP, IMS, and IMP.
6.5.2.1.d | Program manager | d) Ensure the SEP includes objective SMEs to participate in the PDR.
6.5.2.1.e | Program manager | e) Appoint a PDR chair, in coordination with the systems engineer, no later than 45 days prior to the technical review.
6.5.2.1.f | Program manager | f) Coordinate a preliminary agenda between the program IPT and other acquirer SMEs no later than 30 days prior to the PDR.
6.5.2.2.a | Systems engineer | a) Ensure that the pre-established PDR criteria have been met, including measurement status of the program’s technical metrics that demonstrate acceptable progress and developmental maturity of the system design to achieve a successful PDR.
6.5.2.2.b | Systems engineer | b) Ensure the system allocated baseline and physical architecture are complete and consistent.
6.5.2.2.c | Systems engineer | c) Ensure the set of system elements comprising the preliminary system design can achieve the complete set of system allocated baseline requirements.
6.5.2.2.d | Systems engineer | d) Ensure assessments and risks associated with all design constraints are conducted, documented and provided in the technical review material.
6.5.2.2.e | Systems engineer | e) Ensure verification methods are defined for all decomposed and allocated requirements.
6.5.2.2.f | Systems engineer | f) Ensure risk items associated with allocated requirements are identified and analyzed, and mitigation plans are in place.
6.5.2.2.g | Systems engineer | g) Provide supplier organization(s) the opportunity to participate in the PDR planning.
6.5.2.2.h | Systems engineer | h) Coordinate arrangements for PDR location and support.
6.5.2.2.i | Systems engineer | i) Ensure all of the technical review products whose acceptability criteria are defined in Table 13 are completed for the PDR.
6.5.2.2.j | Systems engineer | j) Ensure the preparation of all presentation material is coordinated across IPTs.
6.5.2.2.k | Systems engineer | k) Ensure adequate plans are in place to complete the technical activities to proceed from PDR to the CDR.
6.5.2.2.l | Systems engineer | l) Ensure plans to proceed to CDR allow for contingencies.
6.5.2.3.a | PDR chair | a) Determine PDR team membership.
6.5.2.3.b | PDR chair | b) Approve the final PDR agenda.
6.5.2.3.c | PDR chair | c) Identify any final Clause 6 PDR detailed criteria tailoring for the specific program.
6.5.2.3.d | PDR chair | d) Identify any specific elements for in-depth technical review as required.
6.5.4 | PDR closure | Table 16 lists the actions that should be considered for PDR closure. The responsible people listed are those most often tasked with the listed closure actions. The acquirer and supplier may agree to assign the program manager and systems engineer actions to different people or organizations depending on a given program’s organizational structure. Specific actions shall be deleted, modified, or additional items included, in accordance with the acquirer-supplier agreement, to support a given program. Responsibilities shall be assigned to people or organizations in accordance with the acquirer-supplier agreement.
6.5.4.1.a | Program manager | a) Manage and approve changes to technical baselines resulting from PDR.
6.5.4.1.b | Program manager | b) If funding profiles are insufficient to support development, notify user/sponsor of funding shortfall and request funding profile adjustments.
6.5.4.1.c | Program manager | c) Support preparation of the PDR summary report.
6.5.4.2.a | Systems engineer | a) Determine the root cause of problems, identify corrective actions, and manage to completion.
6.5.4.2.b | Systems engineer | b) Monitor and control the execution of the PDR closure plans.
6.5.4.2.c | Systems engineer | c) Organize and supervise the responses to all action items generated during PDR.
6.5.4.2.d | Systems engineer | d) Support preparation of the PDR summary report.
6.5.4.2.e | Systems engineer | e) Ensure all information products required to be put under configuration control have been delivered to the configuration manager.
6.5.4.2.f | Systems engineer | f) Ensure all IMP and IMS tasks associated with conduct of the PDR have been successfully completed and documented as such.
6.5.4.3.a | PDR chair | a) Ensure preparation of the PDR summary report and formal PDR minutes with the support of the program manager and systems engineer.
6.5.4.3.b | PDR chair | b) Sign off final approval of all action items.
6.5.4.3.c | PDR chair | c) Approve the PDR minutes.
6.5.4.3.d | PDR chair | d) Approve and distribute the PDR summary report.
6.5.4.3.e | PDR chair | e) Prepare and distribute the formal PDR closure letter.
6.5.4.4.a | Recorder | a) Collate all action items for submission to the PDR chair.
6.5.4.4.b | Recorder | b) Prepare the PDR summary report and PDR minutes for signature and distribution by the PDR chair.

## PDR Products Decomposed
|  |  | R = Required to achieve Objective in MVM S = Supports Objective but is not required for MVM | Priority 1 highest, 5 lowest | Requirement | System Requirement | Segment Requirement | Subsystem Requirement | Component Requirement | Interface Requirement | Functional Requirement | Functional Requirement | Performance Requirement | Non-Functional Requirement | Requirement Set | Requirement Flowdown Complete | Requirement Flowdown Partial | Requirement Allocation Complete | Requirement Allocation Partial | Requirement Verify Complete | Requirement Verify Partial | Element | System Element | Segment Element | Subsystem Element | Component Element | Element Connection | Interface | External Interface | Internal Interface | (Exchange) Item | Data Item | Constraint | Design Constraint | Operational Constraint | Function | State | State Transition | Mode | Mode Transition
1 | 6.5.1 | PDR technical review products acceptability criteria | Table 13 lists the products that should be reviewed at PDR, and the associated acceptability criteria that should form a sufficient basis by which to assess each product’s content as acceptable to support a successful PDR. Specific products and associated acceptability criteria shall be deleted, modified, or additional items included, in accordance with the acquirer-supplier agreement, to support a given program.
64 | 6.5.1.3.b | Technical plans | b) Integrating activities of any lower-level PDRs have occurred; identified issues are documented in action plans. | Assume satisfied
4 | 6.5.1.1.c | System allocated baseline documentation | c) Interoperability functional performance requirements are allocated to all system, segment and subsystem preliminary designs. | 1
5 | 6.5.1.1.d | System allocated baseline documentation | d) Preliminary design satisfies design considerations and demonstrates consistency with a standard implementation framework such as department of defense architecture framework (DoDAF) 2.0 or equivalent. | 1
36 | 6.5.1.1.ii | System allocated baseline documentation | ii) Appropriate margins are established at the segment, subsystem, and component levels as applicable. | 1
37 | 6.5.1.1.jj | System allocated baseline documentation | jj) Requirements allocation and derivation from system to segment, subsystem and component levels are complete, traceable to the preliminary design and all “to be determined” (TBD) items are being tracked to resolution. | 1
38 | 6.5.1.1.kk | System allocated baseline documentation | kk) Interface definitions at the inter-segment and inter-subsystem levels are complete, documented, and traceable to the preliminary design and all TBDs are being tracked to resolution. | 1
41 | 6.5.1.1.nn | System allocated baseline documentation | nn) Key allocated performance requirements are traceable to the system’s preliminary design at the segment, subsystem, and component levels as applicable. | 1
42 | 6.5.1.1.oo | System allocated baseline documentation | oo) Key allocated performance requirement parameters developed and assessed at SFR are implemented in each major subsystem and component preliminary design. | 1
47 | 6.5.1.1.tt | System allocated baseline documentation | tt) Computer system and software logical architecture designs have been established; all computer SWCIs, HWCIs, computer software components (CSCs), and computer software units (CSUs) have been defined. | 1
56 | 6.5.1.1.ccc | System allocated baseline documentation | ccc) System allocated baseline documentation is sufficiently complete and correct to enable detailed design to proceed with proper CM. | 1
57 | 6.5.1.2.a | System functional or allocated baseline documentation | a) Preliminary design (hardware, software, human procedures), including interface descriptions is complete, satisfies all requirements in the system functional baseline and is under CM without any major TBDs or open items. | 1
62 | 6.5.1.2.f | System functional or allocated baseline documentation | f) Bi-directional requirements traceability among functional and allocated baselines and the preliminary design is complete, consistent, and has been approved by all applicable stakeholders. | 1
2 | 6.5.1.1.a | System allocated baseline documentation | a) Analysis of system performance is complete and is assessed to meet requirements traceable to the validated CDD. | 2
6 | 6.5.1.1.e | System allocated baseline documentation | e) System operational functions and environments for the preliminary design are traceable to the supplier’s CONOPS and the allocated baseline. | 2
54 | 6.5.1.1.aaa | System allocated baseline documentation | aaa) System end-to-end data flow is complete and documented in the preliminary design. | 2
107 | 6.5.1.5.a | Program life-cycle cost estimate | a) System cost model has been updated, allocated to lower system element levels, and tracked against targets; production cost model constructed. | 2
108 | 6.5.1.5.b | Program life-cycle cost estimate | b) Updated CARD is consistent with the proposed allocated baseline. | 2
68 | 6.5.1.3.f | Technical plans | f) Plans documenting the system, segment, subsystem, and component V&V approaches are developed for the preliminary design. | 3
69 | 6.5.1.3.g | Technical plans | g) Preliminary V&V plans are traceable to the preliminary design correlating all test objectives, test environments and test resources with allocated requirements. | 3
70 | 6.5.1.3.h | Technical plans | h) Preliminary V&V plans address data acquisition, reduction, analysis and documentation, and success criteria. | 3
48 | 6.5.1.1.uu | System allocated baseline documentation | uu) The preliminary design is consistent with the end-to-end processing capabilities and capacities needed for mission operations as indicated by the system performance analysis results. | 4
50 | 6.5.1.1.ww | System allocated baseline documentation | ww) Software requirements specifications (SRS) and interface requirement specifications (IRS), including verification plans, are complete and baselined for all SWCIs for the planned builds up to this point, and satisfy the system functional requirements. | 4
52 | 6.5.1.1.yy | System allocated baseline documentation | yy) Interface control documents trace all software interface requirements to the SWCIs and CSUs. | 4
53 | 6.5.1.1.zz | System allocated baseline documentation | zz) Preliminary software design has been defined and captured for the builds up to this point. | 4
73 | 6.5.1.3.k | Technical plans | k) Design development planning is completed and baselined. | 4
84 | 6.5.1.3.v | Technical plans | v) Software plans have sufficient content to demonstrate that | 4
85 | 6.5.1.3.v.1 | Technical plans | 1) Computer systems and software design and development approach have been confirmed through analyses, demonstrations, and prototyping in a relevant environment. | 4
86 | 6.5.1.3.v.2 | Technical plans | 2) Software increments have been defined and capabilities allocated to specific increments. | 4
87 | 6.5.1.3.v.3 | Technical plans | 3) Software trade studies addressing COTS, reuse, and other software-related issues are completed. | 4
88 | 6.5.1.3.v.4 | Technical plans | 4) Software development process is defined in a baselined software development plan and reflected in the IMP and IMS. | 4
89 | 6.5.1.3.v.5 | Technical plans | 5) Software development schedules reflect supplier software processes and IMP/IMS software events for current and future development phases. | 4
90 | 6.5.1.3.v.6 | Technical plans | 6) Software development environment and test/integration labs have been established with sufficient fidelity and capacity. | 4
91 | 6.5.1.3.v.7 | Technical plans | 7) Software metrics have been defined and a reporting process has been implemented; metrics are being actively tracked and assessed. | 4
92 | 6.5.1.3.v.8 | Technical plans | 8) Testability requirements―built-in test (BIT), false alarm rate, fault isolation, fault detection―have been identified and the required software support documented as requirements so that they can be tested in the proposed design. | 4
93 | 6.5.1.3.v.9 | Technical plans | 9) TEMP addresses all SWCI plans, test facilities, and test plans, including testing required to support incremental approaches and regression tests. | 4
94 | 6.5.1.3.v.10 | Technical plans | 10) Software development estimates [i.e., size, effort (cost), and schedule] are updated. | 4
95 | 6.5.1.3.w | Technical plans | w) Hardware plans have sufficient content to demonstrate that | 4
96 | 6.5.1.3.w.1 | Technical plans | 1) The hardware design/development approach has been confirmed through analyses, demonstrations, and prototyping in a relevant environment. | 4
97 | 6.5.1.3.w.2 | Technical plans | 2) Hardware trade studies addressing COTS, reuse, and other software-related issues are completed. | 4
98 | 6.5.1.3.w.3 | Technical plans | 3) The major phases of the program’s hardware design and development process are defined in a hardware development plan and reflected in the IMP and IMS. | 4
99 | 6.5.1.3.w.4 | Technical plans | 4) Hardware development schedules reflect supplier hardware processes and IMP/IMS hardware design and development events. | 4
100 | 6.5.1.3.w.5 | Technical plans | 5) Hardware development environment (e.g., computer modeling and design tools) and test/integration labs have been established with sufficient fidelity and capacity. | 4
101 | 6.5.1.3.w.6 | Technical plans | 6) Hardware metrics have been defined and a reporting process has been implemented; metrics are being actively tracked and assessed. | 4
102 | 6.5.1.3.w.7 | Technical plans | 7) R&M and testability requirements―BIT, false alarm rate, fault isolation, fault detection―have been identified and the required hardware support documented as requirements so that they can be tested in the proposed design. Also, requirements for detailed design have been identified such as thermal, vibration, shock environments, and highly accelerated life testing (HALT). | 4
103 | 6.5.1.3.w.8 | Technical plans | 8) TEMP addresses all HWCI plans, test facilities, and test plans, including testing required to support incremental approaches and regression tests. | 4
104 | 6.5.1.3.w.9 | Technical plans | 9) Hardware development estimates [i.e., number of HWCIs, effort (cost) and schedule] are updated. | 4
3 | 6.5.1.1.b | System allocated baseline documentation | b) Trade studies related to the design of the system and its lowest level specified CIs are complete and documented, including the rationale for selection of the preferred alternative. | 5
7 | 6.5.1.1.f | System allocated baseline documentation | f) Preliminary system-level design is producible and assessed to be within the production budget. | 5
8 | 6.5.1.1.g | System allocated baseline documentation | g) Preliminary long lead production requirements are developed and documented. | 5
9 | 6.5.1.1.h | System allocated baseline documentation | h) PM&P allocated requirements are incorporated into the preliminary design. | 5
10 | 6.5.1.1.i | System allocated baseline documentation | i) Mass properties margins (average or complex) are established for PDR and correlated with the preliminary design, including allowable growth allocations and metrics. | 5
11 | 6.5.1.1.j | System allocated baseline documentation | j) SSE, COMSEC, cybersecurity, and PP security requirements are allocated and incorporated into the preliminary design in accordance with DoD policies, directives, and system specifications. | 5
12 | 6.5.1.1.k | System allocated baseline documentation | k) EMI control processes and procedures are developed for the preliminary design, and EMI/EMC allocated requirements are incorporated into the preliminary design. | 5
13 | 6.5.1.1.l | System allocated baseline documentation | l) User interface hardware and software allocated requirements for operators, users, maintainers, and sustainers are incorporated into the preliminary design. | 5
14 | 6.5.1.1.m | System allocated baseline documentation | m) Contamination control processes and procedures are developed for the preliminary design. | 5
15 | 6.5.1.1.n | System allocated baseline documentation | n) Hazardous materials management and pollution prevention allocate requirements are incorporated into the preliminary design. | 5
16 | 6.5.1.1.o | System allocated baseline documentation | o) Data storage analysis identifies reliability, maintainability, and availability requirements for storage systems environments. | 5
17 | 6.5.1.1.p | System allocated baseline documentation | p) The preliminary data storage physical architecture fully addresses elements, including communications and processing capacity. | 5
18 | 6.5.1.1.q | System allocated baseline documentation | q) The data storage logical architecture defines a complete list of data receivers to include both computer and human agents. | 5
19 | 6.5.1.1.r | System allocated baseline documentation | r) The level of user integrity (e.g., access control lists) has been identified that enables the system requirements to be met. | 5
20 | 6.5.1.1.s | System allocated baseline documentation | s) DT&E elements are correlated with the preliminary design. | 5
21 | 6.5.1.1.t | System allocated baseline documentation | t) OT&E allocated requirements are incorporated into the preliminary design. | 5
22 | 6.5.1.1.u | System allocated baseline documentation | u) Assessment of the technical effort and design indicates potential for OT&E success (operationally effective and suitable). | 5
23 | 6.5.1.1.v | System allocated baseline documentation | v) The preliminary design incorporates all survivability, vulnerability, and threat allocated requirements for all categories of expected threats, threat environments and their likelihood of occurrence. | 5
24 | 6.5.1.1.w | System allocated baseline documentation | w) A draft critical technologies list is documented. | 5
25 | 6.5.1.1.x | System allocated baseline documentation | x) All CSIs and CAIs are identified. | 5
26 | 6.5.1.1.y | System allocated baseline documentation | y) System safety allocated requirements are incorporated into the preliminary design. | 5
27 | 6.5.1.1.z | System allocated baseline documentation | z) Preliminary hazard analyses are completed and a prioritized list of safety hazards is documented. | 5
28 | 6.5.1.1.aa | System allocated baseline documentation | aa) ESOH allocated requirements are incorporated into the preliminary design. | 5
29 | 6.5.1.1.bb | System allocated baseline documentation | bb) Functional failure modes, effects, and criticality analysis (FMECA) is completed. | 5
30 | 6.5.1.1.cc | System allocated baseline documentation | cc) R&M allocated requirements are supported by the preliminary design. | 5
31 | 6.5.1.1.dd | System allocated baseline documentation | dd) Program’s reliability growth planning strategy and growth curve supports key program milestones needed to meet the CDD threshold at initial operational test and evaluation (IOT&E), and is adequate to grow to the specification value, considering the test schedule and resources. | 5
32 | 6.5.1.1.ee | System allocated baseline documentation | ee) Results from the R&M analyses are used in O&S cost estimates, availability analyses, provisioning plans (spares and repair parts), and maintenance concept. | 5
33 | 6.5.1.1.ff | System allocated baseline documentation | ff) Environmental qualification requirements are incorporated into the design and are addressed in the requirements traceability documentation. | 5
34 | 6.5.1.1.gg | System allocated baseline documentation | gg) Estimate of system reliability and maintainability is updated, based on engineering analyses, initial test results, or other sources of demonstrated reliability and maintainability. | 5
35 | 6.5.1.1.hh | System allocated baseline documentation | hh) Quality and product assurance allocated requirements are incorporated into the preliminary design. | 5
39 | 6.5.1.1.ll | System allocated baseline documentation | ll) Preliminary ground support equipment designs if applicable are traceable to the system allocated baseline and to the preliminary design. | 5
40 | 6.5.1.1.mm | System allocated baseline documentation | mm) Supportability allocated requirements are incorporated into the preliminary design. | 5
43 | 6.5.1.1.pp | System allocated baseline documentation | pp) All deficiencies identified as a result of any testing performed to date, including those related to technology deficiencies identified at SFR, have been correlated with the applicable portions of the preliminary design, impacts have been assessed, and candidate design changes to correct the deficiencies have been identified. | 5
44 | 6.5.1.1.qq | System allocated baseline documentation | qq) The documented results of any prototyping done to date provide evidence that the technical approach is adequate and the risk levels for the corresponding design approach are acceptable. | 5
45 | 6.5.1.1.rr | System allocated baseline documentation | rr) Prototypes implemented to date correctly implement the corresponding portions of the functional baseline and are consistent with the preliminary physical architecture. | 5
46 | 6.5.1.1.ss | System allocated baseline documentation | ss) The physical and functional interfaces of each prototype implemented to date satisfy the corresponding allocated requirements, and validate the sufficiency of the applicable external interface requirements levied on the system for its interaction with facilities and personnel. | 5
49 | 6.5.1.1.vv | System allocated baseline documentation | vv) Preliminary growth margin requirements are documented for computer resources (memory and storage capacity, processor throughput, communications bandwidth, etc.) | 5
51 | 6.5.1.1.xx | System allocated baseline documentation | xx) Software functionality in the preliminary design is consistent with resources expended per the IMS and the software metrics. | 5
55 | 6.5.1.1.bbb | System allocated baseline documentation | bbb) All required software-related documents are baselined and delivered for the builds up to this point. | 5
58 | 6.5.1.2.b | System functional or allocated baseline documentation | b) System, segment, subsystem, and component-level interfaces are baselined and are under configuration control. | 5
59 | 6.5.1.2.c | System functional or allocated baseline documentation | c) C4I allocations are incorporated into the preliminary design across segments, subsystems, and components. | 5
60 | 6.5.1.2.d | System functional or allocated baseline documentation | d) The threat scenario operational and environmental allocations are incorporated into the preliminary design and are traceable to all segments, subsystems, and components. | 5
61 | 6.5.1.2.e | System functional or allocated baseline documentation | e) Test requirements and test data collected to date for the preliminary design are traceable to operational requirements via specifications and VCRMs. | 5
63 | 6.5.1.3.a | Technical plans | a) Supplier’s SEMP is complete, adequate and aligned with the program SEP. | 5
65 | 6.5.1.3.c | Technical plans | c) Plan to CDR is accurately documented in the SEP and SEMP, as well as in the IMP and IMS. | 5
66 | 6.5.1.3.d | Technical plans | d) Program is properly staffed by both the acquirer and supplier. | 5
67 | 6.5.1.3.e | Technical plans | e) Technical performance measures have been identified to track technical progression of design maturity concern areas. | 5
71 | 6.5.1.3.i | Technical plans | i) Hazardous materials management and pollution prevention processes and procedures are verified and baselined. | 5
72 | 6.5.1.3.j | Technical plans | j) Test bed(s) and test facilities chosen based on the preliminary design are deemed adequate to perform system, segment, subsystem, and interface requirements verification (e.g., for critical HWCIs and SWCIs, arrangements for procuring and scheduling the use of V&V resources―simulators, test beds, test facilities―have been demonstrated). | 5
74 | 6.5.1.3.l | Technical plans | l) Program schedule, as depicted in the updated IMS is executable within acceptable technical and cost risks. | 5
75 | 6.5.1.3.m | Technical plans | m) Program is executable with the existing budget. | 5
76 | 6.5.1.3.n | Technical plans | n) Trade studies and system producibility assessments are under way. | 5
77 | 6.5.1.3.o | Technical plans | o) All critical manufacturing processes have been defined, characterized, and documented. | 5
78 | 6.5.1.3.p | Technical plans | p) Failure reporting and corrective action system (FRACAS) is established. | 5
79 | 6.5.1.3.q | Technical plans | q) Logistics (sustainment) and training systems planning and documentation are sufficiently complete to support the technical review. | 5
80 | 6.5.1.3.r | Technical plans | r) LCSP is approved, including updates on program sustainment development efforts and schedules based on current budgets and firm supportability design features. | 5
81 | 6.5.1.3.s | Technical plans | s) LCSP includes software support requirements. | 5
82 | 6.5.1.3.t | Technical plans | t) LCSP addresses DMS, PM&P guidelines, and counterfeit parts risk management. | 5
83 | 6.5.1.3.u | Technical plans | u) Long-lead and key supply chain elements are identified, to include strategic materials risk. | 5
105 | 6.5.1.4.a | Problem risk assessment | a) Cost, schedule, and technical risks are identified, and mitigation plans are in place. | 5
106 | 6.5.1.4.b | Problem risk assessment | b) Risk management process is in place demonstrated by documented execution results of existing mitigation plans. | 5